## Example_POA&M
#VALUE! |  |  |  | inquiries@intersecinc.com
www.intersecinc.com
Control ID (NIST 800-171) | Requirement Text (short) | Point Value (≤1 or 3*) | Target Completion Date (≤180 days) | Root Cause (concise) | Remediation Action Step | Action Item Owner | Budget / Cost (USD) | Level of Effort (L/M/H) | Milestone Description | Evidence / Artifact Location | Percent Complete (%) | Status (Open / Closed) | Last Updated (YYYY-MM-DD)
AC.L2-3.5.3 | Enforce least privilege on system accounts | 1 | 2025-06-15 | Legacy service accounts run with admin rights | Convert 12 service accounts to gMSA with least privilege | Jane Doe | $2,400 | M | 1. Inventory all service accounts (Due: 2025-05-25) 2. Decommission legacy svc_* accounts (Due: 2025-06-05) 3. Create gMSA and assign restricted rights (Due: 2025-06-15) | Excel inventory; AD screenshot; change tickets | 60 | Open | 2025-05-20

## SMART_CheatSheet
#VALUE! |  |  | inquiries@intersecinc.com
www.intersecinc.com
SMART Criteria | Definition | Guiding Questions | POA&M Example
Specific | Clearly defined action, scope, and outcome. | What exactly will be done? Where? On which systems? | Enable Azure AD MFA for all remote VPN users.
Measurable | Includes objective evidence that proves completion. | How will we know the step is finished? What artifact exists? | Capture sign‑in log screenshot showing MFA success.
Achievable | Realistic with current resources & constraints. | Do we have budget, people, and tooling today? | IT Ops already owns Azure P2 licenses.
Relevant | Directly reduces risk / closes the control gap. | Does this task map to the control’s intent? | MFA mitigates phishing risk tied to AC gaps.
Time-bound | Firm due date ≤ 180‑day POA&M window. | When will this milestone finish (≤ 45‑day spacing)? | Complete by 2025‑06‑12.